## Lines
Region A-H (Corre-sponds to track air files for Region A, B, …) | Google Earth ID | Track Air Line No. on Flight Log | FLIGHT LOG DATE DDMMYYYY (Multiple Listings OK) | Run Start Time HHMM (Multiple Listings OK) | Run Stop Time HHMM (Multiple Listings OK) | NASA Flight Log | Site Description (purple: flight boxes; red: methane) | Site Name/Flight Line | Lat1 | Lon1 | Lat2 | Lon2 | Priority (High=1, red) | AV-NG Status Description (i.e. 1st Aq: 5% cloud, light smoke 2nd Aq: Hazy, some cirrus 3rd Aq: Clear) | AV-NG Status (0= incomplete, pink; 1= cloudy/smokey, yellow; 2=complete, green) | 071919 Quick Look Review CMiller Mhelmlinger | Estimated line count | Distance between lat1/lon1 and lat2/lon2 (km) | Estimated area (km2) [Assume image swath of 3.3 km (17500 ft, 5.4 km AGL)]
A | A1 | 1 | 07062019 07122019 | 0029 2316 | 0033 2322 | 19M013a | ATQ flux tower; CALM Atqasuk | AVng_384A-384Z_FL175 | 70.5305 | -157.4674 | 70.2234 | -157.2116 | 2 | 1st: light currus 2nd: clear above, light haze below | 2 | Confirmed Green, all | 1 | 35.4595 | 117.0163
A | A2 | 2 | 07062019 07122019 | 0036 2219 | 0044 2227 | 19M013a | Box (fly listed FL): Atqasuk | Atqasuk_L001_FL176 | 70.268 | -157.0912 | 70.668 | -156.3759 | 2 | 1st: Clear, very light cirrus 2nd: clear above, some haze below | 2 | Confirmed Green, all | 1 | 51.8266 | 171.0279
A | A3 | 3 | 07062019 07122019 | 0047 2230 | 0056 2238 | 19M013a | Box (fly listed FL): Atqasuk | Atqasuk_L002_FL176 | 70.6808 | -156.4406 | 70.2805 | -157.155 | 2 | 1st: Clear, very light cirrus 2nd: clear above, some haze below | 2 | Confirmed Green, all | 1 | 51.8233 | 171.017
A | A4 | 4 | 07062019 07122019 | 0057 2241 | 0105 2249 | 19M013a | Box (fly listed FL): Atqasuk | Atqasuk_L003_FL176 | 70.2931 | -157.2188 | 70.6936 | -156.5053 | 2 | 1st: Clear, very light cirrus 2nd: light cirrus above, some haze below | 2 | Confirmed Green, all | 1 | 51.82 | 171.0061
A | A5 | 5 | 07062019 07122019 | 0105 2252 | 0114 2300 | 19M013a | Box (fly listed FL): Atqasuk | Atqasuk_L004_FL176 | 70.7063 | -156.5701 | 70.3056 | -157.2827 | 2 | 1st: Clear, very light cirrus 2nd: clear above, some haze below | 2 | Confirmed Green, allS | 1 | 51.8167 | 170.9951
A | A6 | 6 | 07062019 07122019 | 0116 2303 | 0124 2311 | 19M013a | Box (fly listed FL): Atqasuk | Atqasuk_L005_FL176 | 70.3181 | -157.3467 | 70.7191 | -156.635 | 2 | 1st: Clear! 2nd: patchy cirrus above, light haze below | 2 | Confirmed Green does not look fogged in qucik look | 1 | 51.8134 | 170.9842
A | A7 | 7 | 07062019 07132019 | 0023 0021 | 0027 0027 | 19M013a | Atqasuk --> Arctic coast | AVng_393A-393Z_FL175 | 70.9046 | -157.7473 | 70.5804 | -157.4802 | 2 | 1st: Cirrus 2nd: clear above, light haze below | 2 | Confirmed Green | 1 | 37.3521 | 123.2619
A | A8 | 8 | 07062019 07122019 | 2345 2127 | 2350 2130 | 19M013a | Box (fly listed FL): Barrow | Barrow_L001_FL175 | 71.3055 | -156.7796 | 71.1913 | -156.4857 | 2 | 1st: Thin Cirrus, clear below 2nd: clear above, light haze below | 2 | Confirmed Green - best ABOVE imagery of Barrow 071219 confirmed green | 1 | 16.4763 | 54.3718
A | A9 | 9 | 07062019 07122019 | 2351 2122 | 2355 2125 | 19M013a | Box (fly listed FL): Barrow | Barrow_L002_FL175 | 71.2072 | -156.4262 | 71.3216 | -156.7204 | 2 | 1st: Thin Cirrus, clear below 2nd:light cirrus above, light haze below | 2 | 070619 Confirmed Green 071219 confirmed green | 1 | 16.501 | 54.4532
A | A10 | 10 | 07062019 07122019 | 2356 2116 | 0001 2119 | 19M013a | Box (fly listed FL): Barrow | Barrow_L003_FL175 | 71.3378 | -156.6611 | 71.2231 | -156.3665 | 2 | 1st:: Thin Cirrus, clear below 2nd: Clear above, haze below | 2 | 070619 QLNA 071219 confirmed green | 1 | 16.5256 | 54.5345
A | A11 | 11 | 07062019 07122019 | 0002 2111 | 0007 2114 | 19M013a | Box (fly listed FL): Barrow | Barrow_L004_FL175 | 71.239 | -156.3068 | 71.3539 | -156.6017 | 2 | 1st: Thin Cirrus, clear below 2nd: Clear above, light haze below | 2 | Confirmed Green 071219 confirmed green | 1 | 16.5502 | 54.6158
A | A12 | 12 | 07072019 07092019 07102019 | 2017 2016 0109 | 2020 2019 0112 | 19M013a | CALM Council grid; Council flux tower | AVng_347A-347Z_FL176 | 64.9006 | -163.8013 | 64.8065 | -163.6628 | 2 | 1st very light cirrus above, clear below | 2 | 070719 Confirmed green 070919 confirmed green | 1 | 12.3367 | 40.7111
A | A13 | 13 | 07122019 | 2324 | 2327 | 19M013a | CH4 (fly listed FL): Coffee Lake | CoffeeLake_L001_FL175 | 70.4942 | -157.6041 | 70.3479 | -157.5002 | 3 | Clear above, some haze below | 2 | Confirmed Geen | 1 | 16.732 | 55.2157
A | A14 | 14 | 07122019 | 2330 | 2333 | 19M013a | CH4 (fly listed FL): Coffee Lake | CoffeeLake_L002_FL175 | 70.3533 | -157.4279 | 70.4999 | -157.5314 | 3 | Clear above, some haze below | 2 | Confirmed Geen | 1 | 16.7449 | 55.2583
A | A15 | 15 | 07122019 | 2336 | 2339 | 19M013a | CH4 (fly listed FL): Coffee Lake | CoffeeLake_L003_FL175 | 70.5055 | -157.4587 | 70.3588 | -157.3556 | 3 | light cirrus above, light haze below | 2 | Confirmed Geen | 1 | 16.7578 | 55.3009
A | A16 | 16 | 07122019 | 2342 | 2345 | 19M013a | CH4 (fly listed FL): Coffee Lake | CoffeeLake_L004_FL175 | 70.3642 | -157.2832 | 70.5111 | -157.3859 | 3 | clear above, light haze below | 2 | Confirmed Geen | 1 | 16.7708 | 55.3435
A | A17 | 17 | 7122019 | 2348 | 2351 | 19M013a | CH4 (fly listed FL): Coffee Lake | CoffeeLake_L005_FL175 | 70.5166 | -157.313 | 70.3696 | -157.2108 | 3 | light cirrus above, light haze below | 2 | Confirmed Geen | 1 | 16.7837 | 55.3861
A | A18 | 18 | 07062019 07122019 | 0009 2134 | 0013 2136 | 19M013a | CH4 (fly listed FL): Pipeline Lake, Barrow | PipeLake_L001_FL175 | 71.1651 | -156.8399 | 71.2601 | -156.6429 | 3 | 1st: very thin cirrus, clear below 2nd: light cirrus above, slight haze below | 2 | Confirmed Green 071219 confirmed green | 1 | 12.7077 | 41.9354
A | A19 | 19 | 07062019 07122019 | 2339 2139 | 2349 2142 | 19M013a | CH4 (fly listed FL): Pipeline Lake, Barrow | PipeLake_L002_FL175 | 71.2461 | -156.5787 | 71.1511 | -156.7759 | 3 | 1st: light cirrus, clear 2nd: clear above, light haze below | 2 | Confirmed Green 071219 confirmed green | 1 | 12.7086 | 41.9384
A | A20 |  |  |  |  | 19M013a | CH4 (fly listed FL): Pipeline Lake, Barrow | PipeLake_L003_FL175 | 71.1651 | -156.8399 | 71.2601 | -156.6429 | 3 | Same coords as A18 | 2 |  | 1 | 12.7077 | 41.9354
A | A21 | 21 | 07062019 07122019 | 2336 2150 | 2346 2153 | 19M013a | CH4 (fly listed FL): Sukok Lake, Barrow | SukokLake_L001_FL175 | 71.0088 | -156.888 | 71.1032 | -156.8381 | 3 | 1st: Clear, light cirrus 2nd: clear above, little haze below | 2 | Confirmed Green does not look fogged in qucik look 071219 confirmed green | 1 | 10.6459 | 35.1316
A | A22 | 22 | 07062019 07122019 | 0014 2146 | 0017 2148 | 19M013a | CH4 (fly listed FL): Sukok Lake, Barrow | SukokLake_L002_FL175 | 71.0984 | -156.7625 | 71.0043 | -156.8127 | 3 | 1st: Thin cirrus, clear below 2nd: light cirrus above, little haze below | 2 | Confirmed Green both acquistions | 1 | 10.6169 | 35.0357
A | A23 |  |  |  |  | 19M013a | CH4 (fly listed FL): Sukok Lake, Barrow | SukokLake_L003_FL175 | 71.0088 | -156.888 | 71.1032 | -156.8381 | 3 | Identical to A21 at this time | 2 |  | 1 | 10.6459 | 35.1316
A | A24 | 24 | 07042019 07062019 | 1933 0235 | 1943 0245 | 19M013a | Coldfoot, Wiseman | AVng_335D-335Z_FL190 | 66.8993 | -150.5657 | 67.4909 | -149.9843 | 2 | 1st: Broken, Yucky 2nd: Clear, no cirrus | 2 | 1st completely cloudy 0706 collect is 5% clouds but very clear otherwise | 1 | 70.3955 | 232.3052
A | A25 | 25 | 07062019 | 2107 | 2117 | 19M013a | IVO flux tower --> Colville River | AVng_357A-357Z_FL189 | 68.4302 | -155.8227 | 68.884 | -155.0834 | 2 | No clouds, light haze all line, smoke at very end. | 2 | confirmed Green | 1 | 58.6574 | 193.5695
A | A26 | 26 | 07082019 07082019 | 0025 0038 | 0029 0047 | 19M013a | Box (fly listed FL): Kotzebue | Kotzebue_L001_FL176 | 67.4592 | -163.2172 | 66.938 | -162.3727 | 2 | Clear - stopped very early. NGDCS issue | 1 | Yellow for coverage green otherwise both collects | 1 | 68.4365 | 225.8403
A | A27 | 27 | 07082019 | 0004 | 0014 | 19M013a | Box (fly listed FL): Kotzebue | Kotzebue_L002_FL176 | 66.9514 | -162.3191 | 67.4726 | -163.1623 | 2 | Clear - NGDCS issue at end of line | 2 | Confirmed Geen | 1 | 68.3887 | 225.6828
A | A28 | 28 | 07072019 | 2349 | 0000 | 19M013a | Box (fly listed FL): Kotzebue | Kotzebue_L003_FL176 | 67.4859 | -163.1074 | 66.9648 | -162.2654 | 2 | Clear | 2 | Confirmed Green | 1 | 68.341 | 225.5251
A | A29 | 29 | 07072019 | 2328 | 2339 | 19M013a | Box (fly listed FL): Kotzebue | Kotzebue_L004_FL176 | 66.9782 | -162.2117 | 67.4992 | -163.0524 | 2 | Clear - NGDCS issue at end of line | 1 | QLIP QLNA 070719 yellow for issue | 1 | 68.2932 | 225.3675
A | A30 | 30 | 07072019 | 2315 | 2325 | 19M013a | Box (fly listed FL): Kotzebue | Kotzebue_L005_FL176 | 67.5125 | -162.9973 | 66.9916 | -162.1579 | 2 | Clear | 2 | Confirmed Green | 1 | 68.2454 | 225.2098
A | A31 | 31 | 07072019 | 2302 | 2313 | 19M013a | Box (fly listed FL): Kotzebue | Kotzebue_L006_FL176 | 67.005 | -162.1041 | 67.5258 | -162.9421 | 2 | Clear above, little haze below | 2 | Confirmed Green | 1 | 68.1976 | 225.0521
A | A32 | 32 | 07062019 07122019 | 0130 2156 | 0141 2208 | 19M013a | Lake Tusikvoak (SE of Barrow) | AVng_392A-392Z_FL175 | 71.0811 | -156.1775 | 70.4492 | -155.0589 | 2 | 1st: Clear! 2nd: clear above, light haze below | 2 | Confirmed Green both acquistions | 1 | 81.3381 | 268.4156
A | A33 | 33 | 07072019 | 2252 | 2257 | 19M013a | Miller - Noorvik | AVng_354A-354Z_FL175 | 66.8727 | -161.3921 | 66.6067 | -161.1835 | 2 | Clear above, little haze below | 2 | Confirmed Green | 1 | 30.9682 | 102.195
A | A34 | 34 | 07072019 07092019 07102019 | 2034 2137 0215 | 2037 2141 0219 | 19M013a | NGEE-Arctic - Teller watershed transect | AVng_343A-343Z_FL179 | 64.7931 | -166.0585 | 64.6545 | -165.8253 | 2 | 1st: Clear 2nd: Clear above, haze below 3rd: Clear above, haze below | 2 | Confirmed Green 071019 haze just visible in quick looks | 1 | 18.9762 | 62.6215
A | A35 | 35 | 07072019 07092019 07102019 | 2044 2059 0152 | 2055 2115 0208 | 19M013a | NGEE-Arctic - Teller watershed transect (new Lat2/Lon2 Jul24) | AVng_344A-344Z_FL184 | 64.5768 | -166.3776 | 65.183 | -164.765 | 2 | 1st: Clear 2nd: Clear above, haze below 3rd: Clear above, haze below | 2 | QLIP QLNA 070719 070919 071019 Confirmed Green haze just visible in quicklooks | 1 | 101.6682 | 335.5052
A | A36 | 36 | 07072019 07092019 07102019 | 1944 2006 0057 | 1950 1213 0103 | 19M013a | Box (fly listed FL): Nome (NGEE) | NGEE_L001_FL188 | 64.7652 | -164.1656 | 64.8564 | -163.4349 | 2 | 1st: clear above, light haze below 2nd: Clear above, haze below 3rd: Clear above, haze below | 2 | Confirmed Green all acquistions | 1 | 36.0412 | 118.9361
A | A37 | 37 | 07072019 07092019 07102019 | 1952 1957 0048 | 1958 2003 0054 | 19M013a | Box (fly listed FL): Nome (NGEE) | NGEE_L002_FL188 | 64.8803 | -163.4515 | 64.7891 | -164.1818 | 2 | 1st: clear above, light cirrus & haze below 2nd: Clear above, haze below 3rd: Clear above, haze below | 2 | Confirmed Green all acquistions | 1 | 35.9891 | 118.7641
A | A38 | 38 | 07072019 07092019 07102019 | 2000 1948 0039 | 2005 1955 0045 | 19M013a | Box (fly listed FL): Nome (NGEE) | NGEE_L003_FL188 | 64.8131 | -164.198 | 64.9042 | -163.4682 | 2 | 1st: very light cirrus above, clear below 2nd: Clear above, haze below 3rd: Clear above, haze below | 2 | Confirmed Green all acquistions | 1 | 35.937 | 118.592
A | A39 | 39 | 07072019 07092019 07102019 | 2007 1939 0030 | 2013 1945 0036 | 19M013a | Box (fly listed FL): Nome (NGEE) | NGEE_L004_FL188 | 64.9281 | -163.4849 | 64.837 | -164.2143 | 2 | 1st: very light cirrus above, clear below 2nd: Clear above, haze below 3rd: Clear above, haze below | 2 | Confirmed Green both acquistions | 1 | 35.8848 | 118.4199
A | A40 | 40 | 07062019 07122019 | 2131 2354 | 2141 0004 | 19M013a | North Slope south of Atqasuk | AVng_391A-391Z_FL177 | 70.1997 | -157.1763 | 69.5997 | -156.7215 | 2 | 1st: Cirrus above, haze and smoke below 2nd: clear above, some haze below | 2 | Confirmed Green, 071219 QLNA | 1 | 68.9381 | 227.4958
A | A41 | 41 | 0713209 | 0159 | 0206 | 19M013a | Box (fly listed FL): Nuiqsut (Macander) | Macander_L001_FL175 | 70.4375 | -151.1937 | 70.0489 | -150.8979 | 2 | light currus above, haze below | 2 | Confirmed Geen | 1 | 44.621 | 147.2491
A | A42 | 42 | 07132019 | 0209 | 0217 | 19M013a | Box (fly listed FL): Nuiqsut (Macander) | Macander_L002_FL175 | 70.0555 | -150.8274 | 70.4439 | -151.1217 | 2 | light currus above, haze below | 2 | Confirmed Geen | 1 | 44.5756 | 147.0994
A | A43 |  |  |  |  | 19M013a | Prospect Creek, Wiseman | AVng_335A-335D_FL187 | 66.142 | -151.2671 | 66.8993 | -150.5657 | 2 |  | 0 |  | 0 | 89.7567 | 296.1971
A | A44 | 44 | 07062019 07242019 | 0212 2003 | 0232 2013 | 19M013a | Anuktuvuk Fire scar (AirMeth) | AVng_383B-383Z_FL187 | 69.2087 | -150.6703 | 68.7287 | -149.9935 | 2 | 1st: (late start), Light cirrus, light smoke. 2nd: haze/light cirrus | 1 | Yellow for not covering coordinates, but 100% useable, green | 1 | 59.817 | 197.396
A | A45 | 45 | 07062019 | 0202 | 0219 | 19M013a | Anuktuvuk Fire scar (AirMeth) | Avng_383A-383B_FL179 | 69.6028 | -151.2517 | 69.2087 | -150.6703 | 2 | Light currus, light smoke | 2 | Confirmed Green | 1 | 49.3702 | 162.9218
A | A46 | 46 | 07242019 | 2019 | 2026 | 19M013a | Anuktuvuk Fire scar (AirMeth) | AVng_381A-381Z_FL179 | 69.3569 | -151.2632 | 69.4554 | -150.3529 | 2 | strong haze | 1 |  | 1 | 37.2497 | 122.924
A | A47 |  |  |  |  | 19M013a | Anuktuvuk Fire scar (AirMeth) | AVng_382A-382B_FL179 | 69.6243 | -151.1713 | 69.3012 | -150.7042 | 2 |  | 0 |  | 0 | 40.2833 | 132.9348
A | A48 |  |  |  |  | 19M013a | Anuktuvuk Fire scar (AirMeth) | AVng_382B-382Z_FL185 | 69.3012 | -150.7042 | 68.8192 | -150.0358 | 2 |  | 0 |  | 0 | 59.8161 | 197.3932
A | A49 | 49 | 07092019 07102019 | 2050 0143 | 2056 0150 | 19M013a | Kougarok | Kougarok_L001_FL182 | 65.0294 | -165.2002 | 65.2443 | -164.6343 | 2 | 1st: Clear above, haze below 2nd: Clear above, haze below | 2 | 070919 Confirmed green 071019 visible haze in Quick Look | 1 | 35.6472 | 117.6359
A | A50 | 50 | 07092019 07102019 | 2038 0131 | 2045 0139 | 19M013a | Kougarok | Kougarok_L002_FL182 | 65.4976 | -164.65 | 65.0821 | -164.9334 | 2 | 1st: Clear above, haze below 2nd: Clear above, haze below | 2 | 070919 Confirmed green 0710919 visible haze in Quick Look | 1 | 48.0427 | 158.5408
A | A51 | 51 | 07092019 07102019 | 2027 0120 | 2035 0128 | 19M013a | Kougarok | Kougarok_L003_FL182 | 65.0766 | -164.8726 | 65.4906 | -164.5969 | 2 | 1st: Clear above, haze below 2nd: Clear above, haze below | 2 | 070919 Confirmed green 071019 visible haze in Quick Look | 1 | 47.7825 | 157.6822
B | B1 | 1 | 07042019 | 1949 | 1953 | 19M013b | Anaktuvuk Pass | AVng_334A-334Z_FL207 | 67.9198 | -149.8537 | 68.1364 | -149.552 | 2 | Mostly clear, clouds at north end | 0 | 50% Usable at best | 0 | 27.1579 | 89.6209
B | B2 | 2 | 07052019 | 2139 | 2149 | 19M013b | BNZ LTER | AVng_251A-251Z_FL179 | 64.6896 | -148.3966 | 64.7343 | -147.7669 | 2 | CLEAR! | 2 | Confirmed Green | 1 | 30.3198 | 100.0554
B | B3 | 3 | 07052019 | 1752 | 1753 | 19M013b | CH4 (fly listed FL): Vault Lake | AB_CH4_L006_FL072 | 65.0393 | -147.714 | 65.0239 | -147.6867 | 2 | Light cirrus , clear below | 2 | Confirmed Green | 1 | 2.1404 | 7.0635
B | B4 | 4 | 07042019 | 2301 | 2304 | 19M013b | CH4 (fly listed FL): Birch Creek Hotspot | AB_CH4_L008_FL072 | 66.184 | -146.6857 | 66.2923 | -146.4071 | 2 | Some clouds | 1 | 20% CLouds | 1 | 17.3447 | 57.2375
B | B5 | 5 | 07042019 07052019 | 2237 1925 | 2250 1935 | 19M013b | CH4 (fly listed FL): Birch Creek North | BirchCrkN_L001_FL179 | 66.0712 | -146.7003 | 66.7365 | -145.5955 | 2 | 1st: Mostly clear 2nd: CLEAR! | 2 | 070419 Yellwo 20% Clouds 0705 donfirmed green | 1 | 88.8275 | 293.1308
B | B6 | 6 | 07042019 07052019 | 2221 1942 | 2235 1955 | 19M013b | CH4 (fly listed FL): Birch Creek North | BirchCrkN_L002_FL179 | 66.7504 | -145.6479 | 66.0848 | -146.7518 | 2 | 1st: 80% clear, some smoke 2nd: CLEAR! | 2 | 0705 confirmed green | 1 | 88.8169 | 293.0958
B | B7 | 7 | 07042019 | 2203 | 2219 | 19M013b | CH4 (fly listed FL): Birch Creek North | BirchCrkN_L003_FL179 | 66.0983 | -146.8033 | 66.7642 | -145.7004 | 2 | Clear, some smoke | 1 | 20% Clouds | 1 | 88.8063 | 293.0607
B | B8 | 8 | 07042019 | 2150 | 2203 | 19M013b | CH4 (fly listed FL): Birch Creek North | BirchCrkN_L004_FL179 | 66.7781 | -145.7529 | 66.1119 | -146.8549 | 2 | Clear, some smoke (GPS glitch) | 1 | QLIP | 1 | 88.7956 | 293.0256
B | B9 | 9 | 07052019 | 1834 | 1841 | 19M013b | CH4 (fly listed FL): Birch Creek South | BirchCrkS_L001_FL180 | 66.4112 | -146.4183 | 66.0514 | -146.312 | 2 | CLEAR! | 2 | COnfirmed Green | 1 | 40.2899 | 132.9566
B | B10 | 10 | 07052019 | 1825 | 1831 | 19M013b | CH4 (fly listed FL): Birch Creek South | BirchCrkS_L002_FL180 | 66.0543 | -146.2511 | 66.4144 | -146.3566 | 2 | CLEAR! | 2 | COnfirmed Green | 1 | 40.3174 | 133.0474
B | B11 | 11 | 07052019 | 1815 | 1823 | 19M013b | CH4 (fly listed FL): Birch Creek South | BirchCrkS_L003_FL180 | 66.4176 | -146.2948 | 66.0573 | -146.1901 | 2 | CLEAR! | 2 | COnfirmed Green | 1 | 40.3449 | 133.1381
B | B12 | 12 | 07052019 07052019 07062019 07062019 07062019 | 1739 2158 1919 1925 0321 | 1741 2159 1921 1926 0325 | 19M013b | CH4 (fly listed FL): Cranberry and Big Trail Lake (*Please acquire when flying in/out Fairbanks airport, particularly June 29 – July 13; Whenever possible, please let Clayton Elder know of your plans to acquire this line, 405-613-4746, Clayton.D.Elder@jpl.nasa.gov; AVIRIS-NG data for this line needs to be uploaded to JPL via UAF end of day). | AB_CH4_L002_FL072 | 64.9432 | -147.8209 | 64.9023 | -147.8229 | 1 | 1st: Cirrus above, clear below 2nd: Clear with light haze 3rd: Light cirrus, light smoke 4th: Light cirrus, light smoke 5th: High clouds and Low smoke | 2 | 070519 green one small cloud 0705 confirmed green 0706 confirmed green last collect of 0706 is yellow | 1 | 4.5414 | 14.9867
B | B13 |  |  |  |  | 19M013b | CH4 (fly listed FL): Creamer Thermocarst | AB_CH4_L005_FL072 | 64.8719 | -147.7983 | 64.8615 | -147.6761 | 2 |  | 0 |  | 0 | 5.884 | 19.4172
B | B14 |  |  |  |  | 19M013b | CH4 (fly listed FL): Donut and Goldstream Lake | AB_CH4_L003_FL072 | 64.8943 | -147.9374 | 64.9231 | -147.8072 | 2 |  | 0 |  | 0 | 6.9231 | 22.8464
B | B15 | 15 | 07052019 07052019 07062019 07242019 | 1744 2149 1933 2154 | 1747 2152 1935 2157 | 19M013b | CH4 (fly listed FL): Goldstream Valley (**Please acquire this line immediately before or after line B12; Prioritize this flight as early as possible in the flight campaign; Whenever possible, please let Clayton Elder know of your plans to acquire this line, 405-613-4746, Clayton.D.Elder@jpl.nasa.gov; AVIRIS-NG data for this line needs to be uploaded to JPL via UAF end of day). | AB_CH4_L001_FL183 | 64.8879 | -147.9505 | 64.9517 | -147.7254 | 1 | 1st: Cirrus above, clear below 2nd: CLEAR (vague cirrus) 3rd: Light cirrus, light smoke 4th: haze/spotty cumulus | 2 | 070519 Green one small cloud 0705 confirmed green 0706 a few clouds, green/yellow but not over site | 1 | 12.7623 | 42.1156
B | B16 |  |  |  |  | 19M013b | CH4 (fly listed FL): Kilearny Smith Lake | AB_CH4_L004_FL072 | 64.8768 | -147.9633 | 64.8583 | -147.8048 | 2 |  | 0 |  | 0 | 7.7591 | 25.6051
B | B17 | 17 | 07252019 | 2202 | 2220 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L001_FL175 | 68.64 | -135.9117 | 69.052 | -133.4846 | 3 | clear, some haze towards end of line | 2 |  | 1 | 107.621 | 355.1493
B | B18 | 18 | 07252019 | 2222 | 2240 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L002_FL175 | 69.0746 | -133.5141 | 68.6626 | -135.941 | 3 | clear, some haze at beginning | 2 |  | 1 | 107.5286 | 354.8444
B | B19 | 19 | 07252019 | 2242 | 2300 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L003_FL175 | 68.6851 | -135.9704 | 69.0972 | -133.5436 | 3 | clear, haze at end, few small cumulus | 1 |  | 1 | 107.4362 | 354.5395
B | B20 | 20 | 07252019 | 2303 | 2321 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L004_FL175 | 69.1198 | -133.5732 | 68.7076 | -135.9999 | 3 | clear, thin haze at beginning | 2 |  | 1 | 107.3438 | 354.2345
B | B21 | 21 | 07252019 | 2323 | 2341 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L005_FL175 | 68.7301 | -136.0294 | 69.1423 | -133.6029 | 3 | last portion of line has cumulus | 1 |  | 1 | 107.2513 | 353.9294
B | B22 | 22 | 07252019 | 2343 | 0001 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L006_FL175 | 69.1649 | -133.6326 | 68.7526 | -136.0589 | 3 | fisrt portion of line has clouds | 1 |  | 1 | 107.1589 | 353.6243
B | B23 | 23 | 07262019 | 0003 | 0021 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L007_FL175 | 68.7751 | -136.0886 | 69.1875 | -133.6624 | 3 | last portion of line has clouds | 1 |  | 1 | 107.0664 | 353.3191
B | B24 | 24 | 07262019 | 0024 | 0042 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L008_FL175 | 69.21 | -133.6923 | 68.7976 | -136.1183 | 3 | beginning of the line has clouds | 1 |  | 1 | 106.9739 | 353.0139
B | B25 | 25 | 07262019 | 0044 | 0102 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L009_FL175 | 68.8201 | -136.148 | 69.2326 | -133.7222 | 3 | clouds at end of line | 1 |  | 1 | 106.8814 | 352.7085
B | B26 | 26 | 07262019 | 0104 | 0122 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L010_FL175 | 69.2551 | -133.7522 | 68.8426 | -136.1778 | 3 | few clouds at beginning of line | 1 |  | 1 | 106.7888 | 352.4031
B | B27 | 27 | 07262019 | 1540 | 1557 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L011_FL175 | 68.865 | -136.2077 | 69.2777 | -133.7822 | 3 | clear | 2 |  | 1 | 106.6963 | 352.0977
B | B28 | 28 | 07262019 | 1559 | 1617 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L012_FL175 | 69.3002 | -133.8123 | 68.8875 | -136.2376 | 3 | clear | 2 |  | 1 | 106.6037 | 351.7921
B | B29 | 29 | 07262019 | 1617 | 1636 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L013_FL175 | 68.91 | -136.2676 | 69.3227 | -133.8425 | 3 | clear | 2 |  | 1 | 106.5111 | 351.4865
B | B30 | 30 | 07262019 | 1638 | 1656 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L014_FL175 | 69.3453 | -133.8727 | 68.9324 | -136.2976 | 3 | clear | 2 |  | 1 | 106.4184 | 351.1809
B | B31 | 31 | 07262019 | 1658 | 1715 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L015_FL175 | 68.9549 | -136.3277 | 69.3678 | -133.903 | 3 | clear | 2 |  | 1 | 106.3258 | 350.8751
B | B32 | 32 | 07262019 | 1717 | 1735 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L016_FL175 | 69.3903 | -133.9334 | 68.9773 | -136.3579 | 3 | clear | 2 |  | 1 | 106.2331 | 350.5694
B | B33 | 33 | 07262019 | 1737 | 1754 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L017_FL175 | 68.9998 | -136.3881 | 69.4128 | -133.9638 | 3 | clear | 2 |  | 1 | 106.1405 | 350.2635
B | B34 | 34 | 07292019 | 1756 | 1814 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L018_FL175 | 69.4353 | -133.9943 | 69.0222 | -136.4184 | 3 | clear, few clouds at the end | 1 |  | 1 | 106.0477 | 349.9576
B | B35 | 35 | 07292019 | 1816 | 1833 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L019_FL175 | 69.0446 | -136.4488 | 69.4578 | -134.0248 | 3 | cloudy at beginning of line | 1 |  | 1 | 105.955 | 349.6516
B | B36 | 36 | 07272019 | 1948 | 2006 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L020_FL175 | 69.4803 | -134.0555 | 69.0671 | -136.4792 | 3 | clear | 2 |  | 1 | 105.8623 | 349.3455
B | B37 | 37 | 07272019 | 2008 | 2027 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L021_FL175 | 69.0895 | -136.5097 | 69.5028 | -134.0861 | 3 | clear | 2 |  | 1 | 105.7695 | 349.0394
B | B38 | 38 | 07272019 07282019 | 2029 1647 | 2046 1705 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L022_FL175 | 69.5253 | -134.1169 | 69.1119 | -136.5402 | 3 | 1st: clear. 2nd: fog/thin clouds below | 2 |  | 1 | 105.6767 | 348.7332
B | B39 | 39 | 07022019 07272019 07282019 | 2027 2048 1627 | 2034 2107 1642 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L023_FL175 | 69.1343 | -136.5708 | 69.5478 | -134.1477 | 3 | 1st: Started midway, clear to end. 2nd: clear. 3rd: haze, thin cloud above | 2 | Half Useable | 1 | 105.5839 | 348.4269
B | B40 | 40 | 07022019 07272019 | 2018 2109 | 2024 2125 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L024_FL175 | 69.5702 | -134.1785 | 69.1567 | -136.6015 | 3 | 1st: Clear to abort point. 2nd: clear | 2 | Half Useable | 1 | 105.4911 | 348.1206
B | B41 | 41 | 07022019 07272019 | 2011 2127 | 2016 2146 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L025_FL175 | 69.1791 | -136.6322 | 69.5927 | -134.2095 | 3 | 1st: Started Midway, Clear to end. 2nd: c;ear | 2 | Half Useable | 1 | 105.3982 | 347.8142
B | B42 | 42 | 07022019 07272019 | 1944 2149 | 1947 2206 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L026_FL175 | 69.6152 | -134.2405 | 69.2015 | -136.663 | 3 | 1st: Clear at start, aborted early. 2nd: clear | 2 | Only 10% of the line is covered, 30% Useable Second attempt some good data over water | 1 | 105.3054 | 347.5078
B | B43 | 43 | 07022019 07022019 07272019 | 1938 1956 2208 | 1940 2002 2227 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L027_FL175 | 69.2239 | -136.6939 | 69.6376 | -134.2716 | 3 | 1st: Clear at start, aborted early 2nd: Started Midway. 3rd: clear | 2 | Only 10% of the line is covered, 30% Useable Second attempt some good data over water | 1 | 105.2125 | 347.2012
B | B44 | 44 | 07022019 07022019 07262019 | 1932 2004 1837 | 1934 2008 1855 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L028_FL175 | 69.6601 | -134.3027 | 69.2463 | -136.7248 | 3 | 1st: Clear at start, aborted early 2nd: Clear to abort point 3rd: few cumulus near end of line | 1 | Only 10% of the line is covered, 50% Useable | 1 | 105.1196 | 346.8946
B | B45 | 45 | 07022019 07272019 | 1924 2229 | 1927 2246 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L029_FL175 | 69.2687 | -136.7558 | 69.6825 | -134.3339 | 3 | 1st: Same, abort after ~10% of line. 2nd: clear | 2 | Only 10% of the line is covered, 50% Useable, Clouds over Channel | 1 | 105.0267 | 346.588
B | B46 | 46 | 07022019 | 1905 | 1922 | 19M013b | CH4 (fly listed FL): Mackenzie Delta | MackDelta_L030_FL175 | 69.7049 | -134.3651 | 69.2911 | -136.7869 | 3 | OK @ start, bad middle, OK @ end | 0 | Unuseable | 0 | 104.9337 | 346.2813
B | B47 |  |  |  |  | 19M013b | CH4 (fly listed FL): Minto Flats | AB_CH4_L007_FL072 | 64.8902 | -148.9326 | 64.9476 | -149.0032 | 2 |  | 0 |  | 0 | 7.203 | 23.77
B | B48 |  |  |  |  | 19M013b | Chalkyitsik | AVng_325A-325D_FL183 | 66.9202 | -143.5668 | 67.2702 | -141.7003 | 2 |  | 0 |  | 0 | 89.6611 | 295.8817
B | B49 | 49 | 07052019 | 2133 | 2143 | 19M013b | CRREL Tanana River fire scar/legacy lidar | AVng_252A-252Z_FL179 | 64.635 | -148.3474 | 64.7374 | -147.8171 | 2 | CLEAR! | 2 | Confirmed Green | 1 | 27.6675 | 91.3026
B | B50 | 50 | 07042019 07132019 | 2026 0249 | 2032 0255 | 19M013b | Dalton Hwy | AVng_370A-370Z_FL182 | 69.1876 | -148.8152 | 69.4717 | -148.5381 | 2 | 1st: Mostly Cloudy 2nd: light currus above, clear below | 2 | 070419 collect not useable 071219 collect fully green | 1 | 33.4099 | 110.2527
B | B51 |  |  |  |  | 19M013b | Fairbanks (Goetz line) | AB_T01_L004_FL185 | 64.622 | -144.432 | 65.0809 | -142.8934 | 2 |  | 0 |  | 0 | 88.8217 | 293.1116
B | B52 |  |  |  |  | 19M013b | Fairbanks (Goetz line) | AB_T01_L005_FL185 | 65.2338 | -142.5078 | 65.6196 | -144.0771 | 2 |  | 0 |  | 0 | 84.2989 | 278.1864
B | B53 |  |  |  |  | 19M013b | Fairbanks (Goetz line) | AB_T01_L006_FL185 | 65.378 | -144.0398 | 64.5275 | -143.8475 | 2 |  | 0 |  | 0 | 94.9987 | 313.4956
B | B54 |  |  |  |  | 19M013b | Fairbanks (Goetz line) | Fairban_L001_FL180 | 65.5085 | -145.2276 | 65.1305 | -147.538 | 2 |  | 0 |  | 0 | 115.2066 | 380.1817
B | B55 | 55 | 07022019 07272019 07272019 | 2057 2256 2325 | 2100 2259 2328 | 19M013b | Box (fly listed FL): Hershel Island | HershIsland_L001_FL177 | 69.5087 | -139.1346 | 69.5891 | -138.8348 | 2 | 1st: Clear below, cirrus above. 2nd: clear above, haze below. 3rd: haze | 2 | No clouds below but cirrus above | 1 | 14.6775 | 48.4356
B | B56 | 56 | 07022019 07272019 | 2102 2319 | 2105 2323 | 19M013b | Box (fly listed FL): Hershel Island | HershIsland_L002_FL177 | 69.6088 | -138.8785 | 69.5283 | -139.1786 | 2 | 1st: Clear below, cirrus above to sun. 2nd: clear above, haze below | 2 | No clouds below but cirrus above | 1 | 14.6839 | 48.4569
B | B57 | 57 | 07022019 07272019 | 2107 2314 | 2119 2317 | 19M013b | Box (fly listed FL): Hershel Island | HershIsland_L003_FL177 | 69.5479 | -139.2227 | 69.6285 | -138.9224 | 2 | 1st: Clear below, cirrus above to sun. 2nd: clear above, haze below | 2 | No clouds below but cirrus above | 1 | 14.6904 | 48.4783
B | B58 | 58 | 07022019 07272019 | 2112 2308 | 2115 2312 | 19M013b | Box (fly listed FL): Hershel Island | HershIsland_L004_FL177 | 69.6481 | -138.9663 | 69.5675 | -139.2668 | 2 | 1st: Clear below, cirrus above to sun. 2nd: clear above, haze below | 2 | No clouds below but cirrus above | 1 | 14.6968 | 48.4996
B | B59 | 59 | 07022019 07272019 | 2117 2303 | 2120 2306 | 19M013b | Box (fly listed FL): Hershel Island | HershIsland_L005_FL177 | 69.587 | -139.3111 | 69.6678 | -139.0103 | 2 | 1st: Clear below, cirrus above. 2nd: clear above, haze below | 2 | No clouds below but cirrus above | 1 | 14.7033 | 48.5209
B | B60 | 60 | 07042019 07132019 | 2017 0258 | 2023 0304 | 19M013b | Imnaviat | AVng_371A-371Z_FL187 | 68.7989 | -148.8183 | 69.1315 | -148.8333 | 2 | 1st: Some clouds, 50% coverage 2nd: light currus above, clear below | 2 | 040719 50% Useable at best, 071319 collect green | 1 | 36.9884 | 122.0618
B | B61 | 61 | 07272019 07282019 | 0020 1738 | 0029 1746 | 19M013b | Inuvik (black carbon) | Inuvik_L001_FL180 | 68.4416 | -134.2852 | 68.2505 | -133.2518 | 3 | 1st: cloudy. 2rd: clear | 2 |  | 1 | 47.4292 | 156.5163
B | B62 | 62 | 07282019 | 1759 | 1812 | 19M013b | Inuvik (black carbon) | Inuvik_L002_FL180 | 67.4281 | -133.0071 | 67.6957 | -134.6454 | 3 | some cirrus/haze | 1 |  | 1 | 75.6268 | 249.5685
B | B63 | 63 | 07282019 | 1817 | 1822 | 19M013b | Inuvik (black carbon) | Inuvik_L003_FL180 | 67.5161 | -133.436 | 67.4219 | -133.855 | 3 | some cirrus/haze | 1 |  | 1 | 20.6996 | 68.3087
B | B64 |  |  |  |  | 19M013b | Inuvik (black carbon) | Inuvik_L004_FL180 | 67.4922 | -134.7055 | 67.1357 | -135.0375 | 3 |  | 0 |  | 0 | 42.1196 | 138.9947
B | B65 |  |  |  |  | 19M013b | Inuvik (black carbon) | Inuvik_L005_FL180 | 67.2366 | -135.4517 | 67.1244 | -136.1081 | 3 |  | 0 |  | 0 | 30.9376 | 102.094
B | B66 | 66 | 07282019 | 1727 | 1730 | 19M013b | Inuvik tall tower, Havipak flux tower | AVng_199A-199Z_FL179 | 68.3137 | -133.5578 | 68.3518 | -133.353 | 2 | clear | 2 |  | 1 | 9.4162 | 31.0734
B | B67 | 67 | 07262019 | 0126 | 0133 | 19M013b | Marsh - Trail Valley Creek; CALM - Parsons Lake | AVng_314A-314Z_FL177 | 68.6522 | -133.6763 | 69.0097 | -133.534 | 2 | clear | 2 |  | 1 | 40.1587 | 132.5237
B | B68 | 68 | 07262019 07272019 07282019 | 1525 0007 1717 | 1532 0013 1723 | 19M013b | Meters-Smith/Marsh; Trail Valley Creek flux tower | AVng_198A-198Z_FL177 | 68.5643 | -133.6122 | 68.8555 | -133.4438 | 2 | 1st: clouds at the beginning of line. 2nd: clear. 3rd: clear | 2 |  | 1 | 33.085 | 109.1804
B | B69 | 69 | 07052019 | 1756 | 1800 | 19M013b | NEON CPCRW box | AVng_258A-258Z_FL190 | 65.2429 | -147.4953 | 65.1125 | -147.4909 | 2 | Some Cirrus, mostly clear | 2 | Green/Yellow depends on NEON box and clouds | 1 | 14.5017 | 47.8557
B | B70 |  |  |  |  | 19M013b | NEON CPCRW box; CRREL Goldstream PF | AVng_253A-253Z_FL183 | 64.9771 | -148.1341 | 64.8556 | -147.638 | 2 |  | 0 |  | 0 | 27.0103 | 89.1341
B | B71 | 71 | 07052019 | 2013 | 2023 | 19M013b | NEON CPCRW box; CRREL Goldstream PF | AVng_254A-254Z_FL183 | 64.8568 | -147.8751 | 64.9603 | -147.5437 | 2 | Heavy Cirrus, clear below | 1 | Confirmed (DARK QUICK LOOK) | 1 | 19.4067 | 64.042
B | B72 | 72 | 07042019 07132019 | 1959 0306 | 2005 0312 | 19M013b | NEON Toolik - Imnaviat Creek | AVng_372A-372Z_FL203 | 68.4994 | -149.6765 | 68.6977 | -148.9983 | 2 | 1st: Mostly Clouds and Shadows 2nd: light currus above, clear below | 2 | 070419 Unuseable, greater than 50% cloud, 071319 collect green | 1 | 35.2608 | 116.3606
B | B73 | 73 | 07042019 07132019 | 2010 0318 | 2014 0321 | 19M013b | NEON Toolik Lake box | AVng_373A-373Z_FL202 | 68.7083 | -149.4242 | 68.5784 | -149.2789 | 2 | 1st: Some clouds, 60% clear 2nd: clear above, clear below | 2 | 070419 collect about 30% cloud cover, 071319 collect green | 1 | 15.5943 | 51.4613
B | B74 | 74 | 07132019 | 0233 | 0238 | 19M013b | Schaefer - Deadhorse area ALT points | AB_T01_L003_FL176 | 69.9453 | -148.7554 | 70.1872 | -148.4242 | 2 | light currus above, clear below | 2 | Confirmed Green | 1 | 29.6775 | 97.9357
B | B75 | 75 | 07052019 | 1909 | 1920 | 19M013b | Smith - Fort Yukon | AVng_323A-323Z_FL179 | 66.0929 | -146.4281 | 66.5912 | -145.1061 | 2 | CLEAR! | 2 | Confirmed Green | 1 | 80.9271 | 267.0595
B | B76 | 76 | 07032019 07042019 07052019 | 0027 2115 1842 | 0030 2130 1849 | 19M013b | Smith - Yukon Flats 1 | AVng_321A-321B_FL178 | 66.1448 | -147.1518 | 66.4252 | -146.6056 | 2 | 1st: Var. Cirrus above, mostly clr below. 2nd: Few Clouds, good line 3rd: CLEAR! | 2 | 1st collect Not Good 070519 cllect confirmed green | 1 | 39.6113 | 130.7174
B | B77 | 77 | 07042019 | 2115 | 2130 | 19M013b | Smith - Yukon Flats 1 | AVng_321B-321Z_FL178 | 66.4252 | -146.6056 | 66.8449 | -145.7574 | 2 | Few Clouds, good line | 2 | Yellow/Green: 20% Clouds coverage mostly useable | 1 | 59.8021 | 197.347
B | B78 | 78 | 07042019 07052019 | 2133 1852 | 2147 1901 | 19M013b | Smith - Yukon Flats 2 | AVng_322A-322B_FL179 | 66.0729 | -146.8995 | 66.4931 | -146.0648 | 2 | 1st: Many clouds at south end 2nd: CLEAR! | 2 | 0704 line is yellow 0705 line confirmed green | 1 | 59.804 | 197.3532
B | B79 | 79 | 07042019 | 2133 | 2147 | 19M013b | Smith - Yukon Flats 2 | AVng_322B-322Z_FL179 | 66.4931 | -146.0648 | 66.7747 | -145.4843 | 2 | Many clouds at south end | 1 |  | 1 | 40.4447 | 133.4677
B | B80 |  |  |  |  | 19M013b | Tundra west of Dalton Hwy | AB_T01_L001_FL187 | 68.7989 | -148.8183 | 69.17 | -148.8326 | 2 |  | 0 |  | 0 | 41.2706 | 136.1931
B | B81 | 81 | 07132019 | 0242 | 0247 | 19M013b | Tundra west of Dalton Hwy | AB_T01_L002_FL178 | 69.6508 | -148.6908 | 69.9275 | -148.7649 | 2 | light currus above, clear below | 2 | Confirmed Green | 1 | 30.8983 | 101.9644
B | B82 |  |  |  |  | 19M013b | Turner - Old Crow Flats | AVng_311A-311Z_FL184 | 67.7427 | -139.8781 | 67.9972 | -139.5939 | 2 |  | 0 |  | 0 | 30.7039 | 101.323
B | B83 |  |  |  |  | 19M013b | Turner - Old Crow Flats | AVng_312A-312Z_FL185 | 68.048 | -139.5219 | 68.3018 | -139.1669 | 2 |  | 0 |  | 0 | 31.8104 | 104.9743
B | B84 | 84 | 07022019 | 1834 | 1837 | 19M013b | Turner - Old Crow Flats | AVng_313A-313Z_FL184 | 67.9222 | -140.0404 | 67.9008 | -139.6029 | 2 | Some Cirrus, Some clouds below | 1 | [Y/A-] Some PopQ, 10% | 1 | 18.4449 | 60.8682
C | C1 |  |  |  |  | 19M013c | Fort Good Hope transect | AVng_307D-307G_FL178 | 67.0621 | -130.4247 | 66.482 | -129.0036 | 2 |  | 0 |  | 0 | 89.6935 | 295.9887
C | C2 |  |  |  |  | 19M013c | Fort Good Hope transect | AVng_307G-307Z_FL176 | 66.482 | -129.0036 | 66.2858 | -128.5445 | 2 |  | 0 |  | 0 | 29.8991 | 98.6669
C | C3 |  |  |  |  | 19M013c | Mackenzie Valley | AVng_308D-308Z_FL179 | 64.1786 | -124.434 | 63.6983 | -123.8817 | 2 |  | 0 |  | 0 | 59.8328 | 197.4481
C | C4 |  |  |  |  | 19M013c | Norman Wells long transect | AVng_190A-190B_FL177 | 65.4734 | -127.6942 | 65.207 | -126.5749 | 2 |  | 0 |  | 0 | 59.7839 | 197.2867
C | C5 |  |  |  |  | 19M013c | Great Bear Lake | GBLake_L001_FL182 | 65.1453 | -123.372 | 65.4646 | -121.7524 | 2 |  | 0 |  | 0 | 83.1917 | 274.5326
C | C6 |  |  |  |  | 19M013c | Great Bear Lake | GBLake_L002_FL182 | 65.4646 | -121.7524 | 65.7148 | -120.3743 | 2 |  | 0 |  | 0 | 69.1688 | 228.2571
C | C7 |  |  |  |  | 19M013c | Great Bear Lake | GBLake_L003_FL182 | 65.7148 | -120.3743 | 66.3001 | -120.2235 | 2 |  | 0 |  | 0 | 65.4388 | 215.9481
C | C8 | 8 | 07182019 | 1830 | 1843 | 19M013c | Great Bear Lake | GBLake_L004_FL182 | 66.3001 | -120.2235 | 65.8683 | -121.4971 | 2 | haze below, very light cirrus above | 2 |  | 1 | 74.8389 | 246.9683
C | C9 | 9 | 07182019 | 1814 | 1827 | 19M013c | Great Bear Lake | GBLake_L005_FL182 | 65.8683 | -121.4971 | 65.432 | -122.7068 | 2 | haze below, very light cirrus above | 2 |  | 1 | 73.6858 | 243.1632
C | C10 | 10 | 07182019 | 1757 | 1812 | 19M013c | Great Bear Lake | GBLake_L006_FL182 | 65.432 | -122.7068 | 64.8745 | -121.3167 | 2 | haze below, very light cirrus above | 2 |  | 1 | 89.7811 | 296.2778
C | C11 | 11 | 07182019 | 1739 | 1753 | 19M013c | Great Bear Lake | GBLake_L007_FL182 | 64.8745 | -121.3167 | 65.414 | -120.0158 | 2 | haze below, very light cirrus above | 2 |  | 1 | 85.4123 | 281.8607
C | C12 | 12 | 07182019 | 1727 | 1732 | 19M013c | Sawmill | Sawmill_L001_FL182 | 65.7166 | -119.0464 | 65.717 | -118.5821 | 2 | 100% cloud coverage | 1 |  | 1 | 21.2326 | 70.0677
C | C13 |  |  |  |  | 19M013c | Indore | Indore_L001_FL182 | 64.8366 | -118.4255 | 64.767 | -118.3291 | 2 |  | 0 |  | 0 | 8.9871 | 29.6575
C | C14 |  |  |  |  | 19M013c | Box (fly listed FL): Port Radium 1 | PortRad1_L001_FL182 | 66.1369 | -117.9794 | 65.9729 | -118.1115 | 2 |  | 0 |  | 0 | 19.1947 | 63.3423
C | C15 |  |  |  |  | 19M013c | Box (fly listed FL): Port Radium 1 | PortRad1_L002_FL182 | 65.9659 | -118.0527 | 66.129 | -117.9209 | 2 |  | 0 |  | 0 | 19.0916 | 63.0024
C | C16 |  |  |  |  | 19M013c | Box (fly listed FL): Port Radium 2 | PortRad2_L001_FL182 | 66.0149 | -118.152 | 65.9793 | -117.7004 | 2 |  | 0 |  | 0 | 20.8077 | 68.6653
C | C17 |  |  |  |  | 19M013c | Box (fly listed FL): Port Radium 2 | PortRad2_L002_FL182 | 66.0036 | -117.6879 | 66.0394 | -118.1406 | 2 |  | 0 |  | 0 | 20.8435 | 68.7836
C | C18 |  |  |  |  | 19M013c | Box (fly listed FL): INAC 2 | INAC2_L001_FL182 | 65.6211 | -118.1841 | 65.5581 | -117.8952 | 2 |  | 0 |  | 0 | 15.0069 | 49.5228
C | C19 |  |  |  |  | 19M013c | Box (fly listed FL): INAC 2 | INAC2_L002_FL182 | 65.5802 | -117.8672 | 65.6431 | -118.1559 | 2 |  | 0 |  | 0 | 14.9859 | 49.4535
D | D1 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L001_FL176 | 69.3194 | -104.7684 | 69.1236 | -103.6735 | 2 |  | 0 |  | 0 | 48.3704 | 159.6223
D | D2 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L002_FL176 | 69.1459 | -103.642 | 69.3417 | -104.737 | 2 |  | 0 |  | 0 | 48.3337 | 159.5012
D | D3 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L003_FL176 | 69.364 | -104.7054 | 69.1681 | -103.6104 | 2 |  | 0 |  | 0 | 48.297 | 159.3801
D | D4 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L004_FL176 | 69.1903 | -103.5788 | 69.3863 | -104.6738 | 2 |  | 0 |  | 0 | 48.2603 | 159.259
D | D5 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L005_FL176 | 69.4086 | -104.6421 | 69.2126 | -103.5471 | 2 |  | 0 |  | 0 | 48.2236 | 159.1378
D | D6 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L006_FL176 | 69.2348 | -103.5154 | 69.4309 | -104.6104 | 2 |  | 0 |  | 0 | 48.1869 | 159.0167
D | D7 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L007_FL176 | 69.4532 | -104.5785 | 69.257 | -103.4836 | 2 |  | 0 |  | 0 | 48.1501 | 158.8954
D | D8 |  |  |  |  | 19M013d | Box (fly listed FL): Cambridge Bay North | CambrBayN_L008_FL176 | 69.2793 | -103.4517 | 69.4755 | -104.5467 | 2 |  | 0 |  | 0 | 48.1134 | 158.7742
D | D9 | 9 | 08012019 | 1517 | 1530 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_9) | CambrBayS_L001_FL176 | 69.2411 | -105.5291 | 68.8819 | -103.533 | 2 | Some clouds above; additional flight: some clouds and shadows | 2 |  | 1 | 88.8012 | 293.044
D | D10 | 10 | 08012019 | 1534 | 1548 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_10) | CambrBayS_L002_FL176 | 69.2609 | -105.4831 | 68.904 | -103.5011 | 2 | scattered; additional flight: some haze, clouds, and shadows | 2 |  | 1 | 88.1148 | 290.7787
D | D11 | 11 | 08012019 | 1550 | 1605 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_11) | CambrBayS_L003_FL176 | 69.2846 | -105.46 | 68.9269 | -103.4734 | 2 | scattered - cloudy at end; additional flight: some haze and shadows | 2 |  | 1 | 88.2492 | 291.2224
D | D12 | 12 | 08012019 | 1607 | 1621 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_12) | CambrBayS_L004_FL176 | 69.306 | -105.4231 | 68.9478 | -103.4347 | 2 | scattered - cloudy at start; additional flight: some haze and shadows | 2 |  | 1 | 88.2696 | 291.2897
D | D13 | 13 | 08012019 | 1623 | 1632 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_13) | CambrBayS_L005_FL176 | 69.3288 | -105.3946 | 68.97 | -103.4029 | 2 | some clouds above at start, scattered below; additional flight: some haze | 2 |  | 1 | 88.3461 | 291.5422
D | D14 | 14 | 08012019 |  |  | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_14) | CambrBayS_L006_FL176 | 69.3511 | -105.3633 | 68.9922 | -103.3713 | 2 | some clouds and shadows | 2 |  | 1 | 88.2898 | 291.3564
D | D15 | 15 | 08012019 |  |  | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_15) | CambrBayS_L007_FL176 | 69.3744 | -105.3369 | 69.0147 | -103.3413 | 2 | some shadows | 2 |  | 1 | 88.3797 | 291.6529
D | D16 | 16 | 08012019 |  |  | 19M013d | Box (fly listed FL): Cambridge Bay South | CambrBayS_L008_FL176 | 69.0727 | -103.4999 | 69.3731 | -105.1683 | 2 | some shadows | 2 |  | 1 | 73.7965 | 243.5283
D | D17 | 17 | 08012019 | 1501 | 1512 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_23) | CambrBayS_L009_FL176 | 69.2203 | -105.5588 | 68.9383 | -103.9811 | 2 | clear | 2 |  | 1 | 70.0492 | 231.1623
D | D18 | 18 | 08012019 | 1446 | 1459 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_24) | CambrBayS_L010_FL176 | 69.2001 | -105.5908 | 68.9178 | -104.0114 | 2 | clear | 2 |  | 1 | 70.174 | 231.5744
D | D19 | 19 | 08012019 | 1433 | 1443 | 19M013d | Box (fly listed FL): Cambridge Bay South (D5_25) | CambrBayS_L011_FL176 | 69.1816 | -105.6134 | 68.8961 | -104.0235 | 2 | clear (ended early) | 1 |  | 1 | 70.763 | 233.518
D | D20 | 20 | 07182019 | 1614 | 1619 | 19M013d | Daring Lake | Daring_Lake_1 | 64.914 | -111.735 | 64.828 | -111.438 | 2 | 1% clouds below | 1 |  | 1 | 16.9743 | 56.0151
D | D21 | 21 | 07182019 | 1607 | 1610 | 19M013d | Daring Lake | Daring_Lake_2 | 64.802 | -111.67 | 64.905 | -111.497 | 2 | clear | 2 |  | 1 | 14.071 | 46.4342
D | D22 |  |  |  |  | 19M013d | Daring Lake | Daring_Lake_3 | 63.846 | -113.225 | 64.516 | -112.189 | 2 |  | 0 |  | 0 | 89.8172 | 296.3968
D | D23 |  |  |  |  | 19M013d | Daring Lake | Daring_Lake_4 | 64.516 | -112.189 | 64.737 | -111.832 | 2 |  | 0 |  | 0 | 29.8872 | 98.6276
D | D24 | 24 | 07182019 | 1531 | 1543 | 19M013d | Daring Lake | Daring_Lake_5 | 63.789 | -113.35 | 64.458 | -112.317 | 2 | clear above, few clouds below at end | 1 |  | 1 | 89.7018 | 296.0159
D | D25 | 25 | 07182019 | 1548 | 1605 | 19M013d | Daring Lake | Daring_Lake_6 | 64.458 | -112.317 | 64.9 | -111.599 | 2 | clear above, clouds below | 1 |  | 1 | 59.8447 | 197.4874
E | E1 | 1 | 07052019 | 2039 | 2044 | 19M013e | Denali National Park sites | AVng_243A-243Z_FL192 | 63.8806 | -150.2513 | 63.7303 | -149.8969 | 2 | CLEAR! | 2 | Confirmed Green | 1 | 24.1237 | 79.6083
E | E2 | 2 | 07052019 | 2047 | 2050 | 19M013e | Denali National Park sites | AVng_247A-247Z_FL192 | 63.8107 | -150.1327 | 63.8345 | -149.884 | 2 | CLEAR! | 2 | Confirmed Green | 1 | 12.4835 | 41.1957
E | E3 |  |  |  |  | 19M013e | Schaefer - YK Delta lakes | AVng_211A-211B_FL175 | 61.2563 | -163.9065 | 61.2768 | -162.7887 | 2 |  | 0 |  | 0 | 59.7963 | 197.3277
E | E4 |  |  |  |  | 19M013e | Box (fly listed FL): Unalakleet North | UnalaklN_L001_FL177 | 63.4343 | -157.945 | 64.0738 | -156.6479 | 2 |  | 0 |  | 0 | 95.5196 | 315.2147
E | E5 |  |  |  |  | 19M013e | Box (fly listed FL): Unalakleet North | UnalaklN_L002_FL177 | 64.0903 | -156.6904 | 63.4509 | -157.9865 | 2 |  | 0 |  | 0 | 95.4578 | 315.0107
E | E6 |  |  |  |  | 19M013e | Box (fly listed FL): Unalakleet North | UnalaklN_L003_FL177 | 63.4675 | -158.0282 | 64.1069 | -156.7331 | 2 |  | 0 |  | 0 | 95.3959 | 314.8066
E | E7 |  |  |  |  | 19M013e | Box (fly listed FL): Unalakleet South | UnalaklS_L001_FL177 | 62.7954 | -159.2119 | 63.4315 | -157.9486 | 2 |  | 0 |  | 0 | 95.0718 | 313.7371
E | E8 |  |  |  |  | 19M013e | Box (fly listed FL): Unalakleet South | UnalaklS_L002_FL177 | 63.448 | -157.9903 | 62.812 | -159.2526 | 2 |  | 0 |  | 0 | 95.0037 | 313.5121
E | E9 |  |  |  |  | 19M013e | Box (fly listed FL): Unalakleet South | UnalaklS_L003_FL177 | 62.8286 | -159.2933 | 63.4645 | -158.0321 | 2 |  | 0 |  | 0 | 94.9355 | 313.2871
E | E10 |  |  |  |  | 19M013e | Box (fly listed FL): YK Delta | YKDelta_L001_FL175 | 61.2187 | -163.7867 | 61.2226 | -161.9605 | 2 |  | 0 |  | 0 | 97.7576 | 322.6
E | E11 |  |  |  |  | 19M013e | Box (fly listed FL): YK Delta | YKDelta_L002_FL175 | 61.2475 | -161.9598 | 61.2436 | -163.7869 | 2 |  | 0 |  | 0 | 97.7327 | 322.518
E | E12 |  |  |  |  | 19M013e | Box (fly listed FL): YK Delta | YKDelta_L003_FL175 | 61.2686 | -163.7872 | 61.2724 | -161.9591 | 2 |  | 0 |  | 0 | 97.7078 | 322.4359
E | E13 |  |  |  |  | 19M013e | Box (fly listed FL): YK Delta | YKDelta_L004_FL175 | 61.2973 | -161.9584 | 61.2935 | -163.7875 | 2 |  | 0 |  | 0 | 97.6829 | 322.3537
E | E14 |  |  |  |  | 19M013e | Box (fly listed FL): YK Delta | YKDelta_L005_FL175 | 61.3184 | -163.7877 | 61.3223 | -161.9576 | 2 |  | 0 |  | 0 | 97.658 | 322.2715
E | E15 |  |  |  |  | 19M013e | Box (fly listed FL): YK Delta | YKDelta_L006_FL175 | 61.3472 | -161.9569 | 61.3433 | -163.788 | 2 |  | 0 |  | 0 | 97.6331 | 322.1892
F | F1 | 1 | 07052019 | 2039 | 2049 | 19M013f | Denali National Park sites | AVng_246A-246Z_FL193 | 63.7689 | -150.266 | 63.8029 | -149.8517 | 2 | CLEAR! | 2 | confirmed Green | 1 | 20.6974 | 68.3015
F | F2 |  |  |  |  | 19M013f | Delta Junction | AVng_256A-256Z_FL191 | 63.9061 | -145.9574 | 63.8255 | -145.5127 | 2 |  | 0 |  | 0 | 23.5519 | 77.7212
F | F3 | 3 | 07052019 | 2033 | 2036 | 19M013f | Healy | AVng_242A-242Z_FL194 | 63.8672 | -149.333 | 63.9011 | -149.0975 | 2 | CLEAR! | 2 | Confirmed Green | 1 | 12.1293 | 40.0267
F | F4 | 2 | 07012019 | 2258 | 2311 | 19M013f | Box (fly listed FL): Kluane Lake | KluaneLak_L001_FL206 | 61.0518 | -138.4263 | 60.4812 | -136.9715 | 2 | Haze, Some Cirrus, Some below | 1 | [Y/A-] Some PopQ, 10% | 1 | 101.323 | 334.3658
F | F5 | 3 | 07012019 | 2240 | 2256 | 19M013f | Box (fly listed FL): Kluane Lake | KluaneLak_L002_FL206 | 60.5007 | -136.9398 | 61.0717 | -138.3954 | 2 | Haze, Some Cirrus, Alto-Cumulus at end | 1 | [Y/A-] Some PopQ, 10% | 1 | 101.3506 | 334.4569
F | F6 | 4 | 07012019 | 2205 | 2222 | 19M013f | Box (fly listed FL): Kluane Lake | KluaneLak_L003_FL206 | 61.0917 | -138.3645 | 60.5201 | -136.9082 | 2 | Haze, Some puffs below | 1 | [Y/A-] Some PopQ, 10% | 1 | 101.3782 | 334.548
F | F7 | 5 | 07012019 | 2225 | 2238 | 19M013f | Box (fly listed FL): Kluane Lake | KluaneLak_L004_FL206 | 60.5395 | -136.8765 | 61.1116 | -138.3335 | 2 | Haze, Some Cirrus, Some puffs below, Shadows | 1 | [Y/C] 40% Cloud Cover | 1 | 101.4058 | 334.639
F | F8 | 6 | 07012019 | 2314 | 2317 | 19M013f | Box (fly listed FL): Kluane Lake | KluaneLak_L005_FL206 | 61.1315 | -138.3025 | 60.559 | -136.8447 | 2 | Haze, More Clouds, Early Abort | 0 | [Y/C] 30% Cloud Cover, but short line | 0 | 101.4333 | 334.73
F | F9 | 7 | 07012019 |  |  | 19M013f | Box (fly listed FL): Kluane Lake | KluaneLak_L006_FL206 | 60.5784 | -136.8129 | 61.1515 | -138.2715 | 2 |  | 0 |  | 0 | 101.4609 | 334.8209
G | G1 | 1 | 07192019 | 0053 | 0057 | 19M013g | CFS Fuel inventory plots/burn scar - Mackenzie Hwy | AVng_172A-172Z_FL183 | 62.4995 | -116.518 | 62.3401 | -116.4977 | 2 | 1st: clear. 2nd: haze below | 2 |  | 1 | 17.7535 | 58.5866
G | G2 | 2 | 07182019 | 2257 | 2304 | 19M013g | Box (fly listed FL): Hayes River | HayesRiv_L001_FL182 | 60.766 | -115.8226 | 60.5062 | -116.2158 | 2 | haze below | 2 |  | 1 | 35.9748 | 118.7169
G | G3 | 3 | 07182019 | 2248 | 2254 | 19M013g | Box (fly listed FL): Hayes River | HayesRiv_L002_FL182 | 60.4912 | -116.1753 | 60.7513 | -115.7815 | 2 | haze below | 2 |  | 1 | 36.0216 | 118.8712
G | G4 | 4 | 07142019 07142019 | 1743 1759 | 1757 1812 | 19M013g | Mackenzie Valley into Fort Simpson | AVng_194A-194Z_FL181 | 62.3341 | -122.6738 | 61.8937 | -121.3997 | 2 | 1st: Clear, very light haze 2nd: Clear, very light haze | 2 |  | 1 | 82.3856 | 271.8726
G | G5 | 5 | 07142019 | 1836 | 1844 | 19M013g | Box (fly listed FL): Scotty Creek | ScottyCrk _L001_FL183 | 61.6556 | -121.4675 | 61.247 | -121.3449 | 2 | Clear, very light haze | 2 |  | 1 | 45.8891 | 151.434
G | G6 | 6 | 07142019 | 1825 | 1833 | 19M013g | Box (fly listed FL): Scotty Creek | ScottyCrk _L002_FL183 | 61.2507 | -121.2937 | 61.6593 | -121.4156 | 2 | Clear, very light haze | 2 |  | 1 | 45.8886 | 151.4323
G | G7 | 7 | 07142019 | 1945 | 1953 | 19M013g | Box (fly listed FL): Scotty Creek | ScottyCrk _L003_FL183 | 61.6629 | -121.3637 | 61.2544 | -121.2424 | 2 | Clear | 2 |  | 1 | 45.888 | 151.4306
G | G8 | 8 | 07142019 | 1814 | 1822 | 19M013g | Box (fly listed FL): Scotty Creek | ScottyCrk _L004_FL183 | 61.258 | -121.1912 | 61.6666 | -121.3117 | 2 | Clear, very light haze | 2 |  | 1 | 45.8875 | 151.4288
G | G9 | 9 | 07142019 | 1957 | 2008 | 19M013g | Yellowknife - Fort Simpson transect | AVng_195A-195D_FL191 | 61.8931 | -121.0866 | 62.0622 | -119.761 | 2 | Clear, light clouds at end of line | 1 |  | 1 | 71.7581 | 236.8016
G | G10 |  |  |  |  | 19M013g | Yellowknife - Fort Simpson transect | AVng_195D-195G_FL195 | 62.0622 | -119.761 | 62.2555 | -118.0845 | 2 | Clear, light clouds at end of line | 1 |  | 1 | 89.671 | 295.9142
G | G11 | 11 | 07192019 | 0035 | 0050 | 19M013g | Yellowknife - Fort Simpson transect | AVng_195G-195K_FL183 | 62.2555 | -118.0845 | 62.4284 | -116.3876 | 2 | 1st: Clear, light clouds at end of line. 2nd: haze below | 2 |  | 1 | 89.6688 | 295.9069
G | G12 | 12 | 07192019 | 0059 | 0112 | 19M013g | Yellowknife - Fort Simpson transect | AVng_195K-195Z_FL181 | 62.4284 | -116.3876 | 62.5613 | -114.9018 | 2 | 1st: clear. 2nd: light haze/smoke plume | 2 |  | 1 | 77.7148 | 256.459
G | G13 | 13 | 07142019 07182019 | 1912 1705 | 1917 1707 | 19M013g | Fort Liard | Ft_Liard_L001_FL183 | 60.3018 | -123.5426 | 60.1351 | -123.2221 | 2 | 1st: Clear. 2nd: clear | 2 |  | 1 | 25.6253 | 84.5634
G | G14 | 14 | 07142019 | 1903 | 1907 | 19M013g | Box (fly listed FL): Fort Liard | Ft_Liard_L002_FL183 | 60.3303 | -123.282 | 60.1986 | -123.4418 | 2 | Clear | 2 |  | 1 | 17.097 | 56.4202
G | G15 | 15 | 07142019 | 1921 | 1925 | 19M013g | Box (fly listed FL): Fort Liard | Ft_Liard_L003_FL183 | 60.2111 | -123.4871 | 60.3431 | -123.3271 | 2 | Clear | 2 |  | 1 | 17.1258 | 56.5151
G | G16 |  |  |  |  | 19M013g | Box (fly listed FL): Fort Resolution | FtResol_L001_FL182 | 61.2656 | -117.504 | 61.0954 | -117.504 | 2 |  | 0 |  | 0 | 18.9319 | 62.4752
G | G17 |  |  |  |  | 19M013g | Box (fly listed FL): Fort Resolution | FtResol_L002_FL182 | 61.0953 | -117.4524 | 61.2657 | -117.4522 | 2 |  | 0 |  | 0 | 18.9515 | 62.5398
G | G18 |  |  |  |  | 19M013g | Box (fly listed FL): Kakisa Lake | KakisaLake_L001_FL182 | 60.9183 | -117.1046 | 60.6821 | -116.3284 | 2 |  | 0 |  | 0 | 49.6235 | 163.7577
G | G19 | 19 | 07192019 | 0009 | 0013 | 19M013g | Box (fly listed FL): Kakisa Lake | KakisaLake_L002_FL182 | 60.7033 | -116.3018 | 60.9395 | -117.0777 | 2 | haze below | 2 |  | 1 | 49.5844 | 163.6284
G | G20 | 20 | 07192019 | 0003 | 0007 | 19M013g | Box (fly listed FL): Kakisa Lake | KakisaLake_L003_FL182 | 60.9607 | -117.0507 | 60.7246 | -116.2751 | 2 | haze below | 2 |  | 1 | 49.5452 | 163.4991
G | G21 | 21 | 07182019 | 2351 | 0000 | 19M013g | Box (fly listed FL): Kakisa Lake | KakisaLake_L004_FL182 | 60.7458 | -116.2484 | 60.9819 | -117.0237 | 2 | haze below | 2 |  | 1 | 49.506 | 163.3697
G | G22 | 22 | 07182019 | 2340 | 2349 | 19M013g | Box (fly listed FL): Kakisa Lake | KakisaLake_L005_FL182 | 61.0031 | -116.9967 | 60.767 | -116.2217 | 2 | haze below | 2 |  | 1 | 49.4668 | 163.2403
G | G23 | 23 | 07182019 | 2330 | 2338 | 19M013g | Box (fly listed FL): Hay River | HayRiver_L001_FL182 | 60.6038 | -115.0024 | 60.8732 | -113.9328 | 2 | haze below | 2 |  | 1 | 65.3989 | 215.8165
G | G24 | 24 | 07182019 | 2318 | 2327 | 19M013g | Box (fly listed FL): Hay River | HayRiver_L002_FL182 | 60.8952 | -113.9571 | 60.626 | -115.0252 | 2 | haze below | 2 |  | 1 | 65.2794 | 215.4219
G | G25 | 25 | 07182019 | 2307 | 2316 | 19M013g | Box (fly listed FL): Hay River | HayRiver_L003_FL183 | 60.6483 | -115.0481 | 60.9171 | -113.9813 | 2 | haze below | 2 |  | 1 | 65.1598 | 215.0272
G | G26 | 26 | 07182019 | 2231 | 2241 | 19M013g | Box (fly listed FL): Hay River | HayRiver_L004_FL183 | 60.9391 | -114.0056 | 60.6706 | -115.0709 | 2 | haze below | 2 |  | 1 | 65.0402 | 214.6325
G | G27 | 27 | 07182019 | 2217 | 2229 | 19M013g | Box (fly listed FL): Hay River | HayRiver_L005_FL183 | 60.6928 | -115.0938 | 60.9611 | -114.0299 | 2 | haze below | 2 |  | 1 | 64.9205 | 214.2378
G | G28 | 28 | 07182019 | 2204 | 2215 | 19M013g | Great Slave Lake Big Island 1 | AB_Bathy_B01_L001_FL175_BigIsland | 61.06 | -117.175 | 60.891 | -116.162 | 2 | haze below | 2 |  | 1 | 57.7912 | 190.7109
G | G29 | 29 | 07182019 | 2151 | 2202 | 19M013g | Great Slave Lake Big Island 2 | AB_Bathy_B01_L002_FL175_BigIsland | 60.915 | -116.145 | 61.083 | -117.159 | 2 | haze below | 2 |  | 1 | 57.7679 | 190.634
G | G30 | 30 | 07182019 | 2138 | 2148 | 19M013g | Great Slave Lake Big Island 3 | AB_Bathy_B01_L003_FL175_BigIsland | 61.107 | -117.142 | 60.938 | -116.128 | 2 | haze below | 2 |  | 1 | 57.7657 | 190.6268
G | G31 |  |  |  |  | 19M013g | Great Slave Lake Big Island 4 | AB_Bathy_B01_L004_FL175_BigIsland | 60.962 | -116.111 | 61.13 | -117.126 | 2 |  | 0 |  | 0 | 57.7423 | 190.5495
G | G32 |  |  |  |  | 19M013g | Great Slave Lake Big Island 5 | AB_Bathy_B01_L005_FL175_BigIsland | 61.154 | -117.109 | 60.986 | -116.095 | 2 |  | 0 |  | 0 | 57.6522 | 190.2523
G | G33 |  |  |  |  | 19M013g | Great Slave Lake Big Island 6 | AB_Bathy_B01_L006_FL175_BigIsland | 61.009 | -116.078 | 61.178 | -117.093 | 2 |  | 0 |  | 0 | 57.7009 | 190.413
G | G34 |  |  |  |  | 19M013g | Great Slave Lake Big Island 7 | AB_Bathy_B01_L007_FL175_BigIsland | 61.201 | -117.076 | 61.033 | -116.061 | 2 |  | 0 |  | 0 | 57.6264 | 190.1672
G | G35 |  |  |  |  | 19M013g | Great Slave Lake Big Island 8 | AB_Bathy_B01_L008_FL175_BigIsland | 61.056 | -116.044 | 61.225 | -117.059 | 2 |  | 0 |  | 0 | 57.6243 | 190.16
G | G36 |  |  |  |  | 19M013g | Great Slave Lake Big Island 9 | AB_Bathy_B01_L009_FL175_BigIsland | 61.249 | -117.043 | 61.08 | -116.027 | 2 |  | 0 |  | 0 | 57.6358 | 190.1982
G | G37 |  |  |  |  | 19M013g | Great Slave Lake Big Island 10 | AB_Bathy_B01_L010_FL175_BigIsland | 61.103 | -116.01 | 61.272 | -117.026 | 2 |  | 0 |  | 0 | 57.5982 | 190.0742
G | G38 |  |  |  |  | 19M013g | Great Slave Lake Big Island 11 | AB_Bathy_B01_L011_FL175_BigIsland | 61.296 | -117.01 | 61.127 | -115.993 | 2 |  | 0 |  | 0 | 57.6097 | 190.1119
G | G39 |  |  |  |  | 19M013g | Great Slave Lake Big Island 12 | AB_Bathy_B01_L012_FL175_BigIsland | 61.15 | -115.976 | 61.319 | -116.993 | 2 |  | 0 |  | 0 | 57.5721 | 189.9878
G | G40 |  |  |  |  | 19M013g | Great Slave Lake Big Island 13 | AB_Bathy_B01_L013_FL175_BigIsland | 61.343 | -116.976 | 61.174 | -115.959 | 2 |  | 0 |  | 0 | 57.5328 | 189.8582
G | G41 |  |  |  |  | 19M013g | Great Slave Lake Big Island 14 | AB_Bathy_B01_L014_FL175_BigIsland | 61.197 | -115.942 | 61.367 | -116.959 | 2 |  | 0 |  | 0 | 57.5308 | 189.8516
G | G42 |  |  |  |  | 19M013g | Great Slave Lake Big Island 15 | AB_Bathy_B01_L015_FL175_BigIsland | 61.39 | -116.943 | 61.221 | -115.925 | 2 |  | 0 |  | 0 | 57.5064 | 189.771
G | G43 |  |  |  |  | 19M013g | Great Slave Lake Big Island 16 | AB_Bathy_B01_L016_FL175_BigIsland | 61.244 | -115.908 | 61.414 | -116.926 | 2 |  | 0 |  | 0 | 57.5043 | 189.7643
H | H1 | 1 | 07152019 | 1748 | 1801 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L001_FL182 | 59.0411 | -111.7317 | 58.3129 | -111.6698 | 2 | Cirrus above halfway through line | 1 |  | 1 | 81.0493 | 267.4627
H | H2 | 2 | 07152019 | 1804 | 1817 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L002_FL182 | 58.314 | -111.6224 | 59.0421 | -111.6833 | 2 | Cirrus above at beginning and halfway through line | 1 |  | 1 | 81.0415 | 267.437
H | H3 | 3 | 07152019 | 1819 | 1833 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L003_FL182 | 59.0432 | -111.6349 | 58.3151 | -111.575 | 2 | few clouds below | 1 |  | 1 | 81.0337 | 267.4113
H | H4 | 4 | 07152019 | 1835 | 1848 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L004_FL182 | 58.3162 | -111.5276 | 59.0442 | -111.5865 | 2 | cirrus above halfway | 1 |  | 1 | 81.0259 | 267.3855
H | H5 | 5 | 07152019 | 1850 | 1904 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L005_FL182 | 59.0453 | -111.5381 | 58.3173 | -111.4802 | 2 | few below | 1 |  | 1 | 81.0181 | 267.3597
H | H6 | 6 | 07152019 07162019 07162019 | 1907 1809 1826 | 1919 1813 1840 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L006_FL182 | 58.3183 | -111.4328 | 59.0463 | -111.4897 | 2 | 1st: few below 2nd: short line due to track air issue 3rd: few clouds at the end of the line | 1 |  | 1 | 81.0102 | 267.3338
H | H7 | 7 | 07152019 07162019 07162019 | 1922 1633 1736 | 1935 1647 1750 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L007_FL182 | 59.0473 | -111.4413 | 58.3194 | -111.3854 | 2 | 1st: few below 2nd: Clear above, haze below - window fogging 3rd: clear above, haze below | 2 |  | 1 | 81.0024 | 267.3079
H | H8 | 8 | 07162019 07162019 | 1600 1705 | 1613 1718 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L008_FL182 | 58.3204 | -111.338 | 59.0482 | -111.3929 | 2 | 1st: ligh haze - window fogging 2nd: clear above, haze below | 2 |  | 1 | 80.9945 | 267.2819
H | H9 | 9 | 07162019 07162019 | 1616 1721 | 1630 1734 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L009_FL182 | 59.0492 | -111.3444 | 58.3214 | -111.2906 | 2 | 1st: ligh haze - window fogging 2nd: clear above, haze below | 2 |  | 1 | 80.9866 | 267.2559
H | H10 | 10 | 07162019 07162019 | 1649 1752 | 1703 1806 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L010_FL182 | 58.3224 | -111.2431 | 59.0501 | -111.296 | 2 | 1st: clear above, haze below 2nd: Clear above, haze below | 2 |  | 1 | 80.9787 | 267.2298
H | H11 | 11 | 07162019 | 1843 | 1957 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L011_FL182 | 59.051 | -111.2476 | 58.3233 | -111.1957 | 2 | few clouds at beginning of line | 1 |  | 1 | 80.9708 | 267.2037
H | H12 |  |  |  |  | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L012_FL182 | 58.3243 | -111.1483 | 59.0519 | -111.1992 | 2 |  | 0 |  | 0 | 80.9629 | 267.1775
H | H13 |  |  |  |  | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L013_FL182 | 59.0528 | -111.1507 | 58.3252 | -111.1009 | 2 |  | 0 |  | 0 | 80.9549 | 267.1513
H | H14 |  |  |  |  | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L014_FL182 | 58.3261 | -111.0534 | 59.0537 | -111.1023 | 2 |  | 0 |  | 0 | 80.947 | 267.125
H | H15 |  |  |  |  | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L015_FL182 | 59.0545 | -111.0539 | 58.327 | -111.006 | 2 |  | 0 |  | 0 | 80.939 | 267.0987
H | H16 | 16 | 07152019 | 1728 | 1741 | 19M013h | Box (fly listed FL): Peace Athabasca Delta | PeaceAth_L016_FL182 | 58.3279 | -110.9586 | 59.0553 | -111.0054 | 2 | Cirrus above, clouds below | 1 |  | 1 | 80.931 | 267.0723
H | H17 | 17 | 07162019 | 2201 | 2205 | 19M013h | Box (fly listed FL): IAC 3 | IAC3 _L001_FL185 | 62.8856 | -113.2426 | 63.0785 | -113.0873 | 2 | clear above, haze below | 2 |  | 1 | 22.8393 | 75.3698
H | H18 | 18 | 07162019 | 2154 | 2158 | 19M013h | Box (fly listed FL): IAC 3 | IAC3 _L002_FL185 | 63.0869 | -113.1391 | 62.8941 | -113.2939 | 2 | clear above, few clouds/haze below | 1 |  | 1 | 22.8169 | 75.2957
H | H19 | 19 | 07162019 | 2147 | 2152 | 19M013h | Box (fly listed FL): IAC 3 | IAC3 _L003_FL185 | 62.9026 | -113.3453 | 63.0953 | -113.191 | 2 | clear above, haze below | 2 |  | 1 | 22.7944 | 75.2216
H | H20 | 20 | 07162017 | 2140 | 2145 | 19M013h | Box (fly listed FL): IAC 3 | IAC3 _L004_FL185 | 63.1036 | -113.2429 | 62.9111 | -113.3968 | 2 | clear above, haze below | 2 |  | 1 | 22.772 | 75.1475
H | H21 | 21 | 07162019 | 2217 | 2224 | 19M013h | Box (fly listed FL): IAC 4 | IAC4 _L001_FL185 | 62.8168 | -113.2754 | 62.5403 | -113.5738 | 2 | clear above, haze below | 2 |  | 1 | 34.3113 | 113.2274
H | H22 | 22 | 07162019 | 2209 | 2215 | 19M013h | Box (fly listed FL): IAC 4 | IAC4 _L002_FL185 | 62.5293 | -113.5254 | 62.8058 | -113.2266 | 2 | clear above, haze below | 2 |  | 1 | 34.3208 | 113.2586
H | H23 | 23 | 07162019 | 2244 | 2249 | 19M013h | Box (fly listed FL): IAC 5 | IAC5 _L001_FL185 | 62.5244 | -113.0119 | 62.313 | -112.7867 | 2 | clear above, haze below | 2 |  | 1 | 26.2091 | 86.49
H | H24 | 24 | 07162019 | 2236 | 2242 | 19M013h | Box (fly listed FL): IAC 5 | IAC5 _L002_FL185 | 62.3242 | -112.7387 | 62.5352 | -112.9632 | 2 | clear above, haze below | 2 |  | 1 | 26.156 | 86.3148
H | H25 | 25 | 07162019 | 2229 | 2234 | 19M013h | Box (fly listed FL): IAC 5 | IAC5 _L003_FL185 | 62.546 | -112.9145 | 62.3353 | -112.6907 | 2 | clear above, haze below | 2 |  | 1 | 26.1029 | 86.1396
X | X | X | X | X | X | X | ABOVE2019-Saskatoon-20 | ang20170816t173853 | 53.5685 | -106.2557 | 53.6604 | -106.1663 | 2 | cumulus and cirrus above | 1 |  | 1 | 11.7983 | 38.9343
X | X | X | X | X | X | X | ABOVE2019-Saskatoon-120 | ang20170814t182454 | 54.006 | -105.2318 | 53.8875 | -104.5315 | 2 | cumulus and cirrus above | 1 |  | 1 | 47.6899 | 157.3765
[17 empty] | Total lines | Total distance of data acquisition (km) | Total area of data acquisition (km2)
[17 empty] | 193 | 15712.131 | 51850.0323